## Executive Summary
SecureDev AI - Product Development Plan 2026
AI-powered Application Security platform that shifts security left by embedding automated security intelligence across the entire SDLC.
12 | 127 | 2 | 74 | 53 | 11 | Feb | Dec
Features | Total Tasks | Phases | Phase 1 Tasks | Phase 2 Tasks | Months | Start | End
Feature ID | Feature Name | Phase | Timeline | Tasks | Total Weight | Description | Value Proposition
F1 | Security Requirements Generation | Phase 1 | Feb - May | 13 | 32 | Auto-generate OWASP/ASVS-aligned security requirements with JIRA & Azure DevOps integration | Eliminates the manual effort of writing security requirements for each project. Ensures consistent coverage against OWASP ASVS 4.0. Cuts requirements phase from 2 weeks to 2 hours.
F2 | Misuse / Abuse Case Generation | Phase 1 | Feb - Apr | 9 | 20 | Generate structured misuse & abuse cases from architecture descriptions with CAPEC/ATT&CK mapping | Bridges the gap between threat modeling and development. Developers get concrete abuse scenarios instead of abstract threat lists.
F3 | Security Acceptance Criteria | Phase 1 | Mar - May | 8 | 17 | BDD/Gherkin acceptance criteria mapped to risks with full traceability | Makes security testable and trackable. QA teams get concrete criteria. Completion can be measured like any other user story.
F4 | AI-Assisted Threat Modeling (L0 & L1) | Phase 1 | Feb - Jun | 11 | 26 | Auto-generate threat models with STRIDE, DFD visualization, and PDF reports | Removes the need for security architects to manually create threat models. Any development team can generate a threat model in minutes instead of days.
F5 | Commit Scanner | Phase 1 | Mar - May | 10 | 22 | Detect secrets in commits with webhooks, entropy detection, and remediation guidance | Prevents credential leaks before they reach production. Reduces secret exposure window from days to seconds.
F6 | Pipeline Policy-as-Code Validator | Phase 1 | Apr - Jun | 11 | 24 | Validate CI/CD pipelines against AppSec policies for GitHub Actions, Jenkins, GitLab CI, Azure Pipelines | Ensures every pipeline has required security gates. Catches missing SAST/SCA/DAST steps before code ships.
F7 | VS Code Plugin (Initial Version) | Phase 1 | Apr - Jun | 10 | 20 | IDE extension for Python & JS/TS with inline security hints and quick-fix remediation | Security feedback at the point of code creation. Developers see issues before commit, not after a scan.
F8 | Full AI Threat Modeling | Phase 2 | Jul - Nov | 12 | 30 | Deep architecture analysis with L0/L1/L2 STRIDE, attack path analysis, NIST/ISO/PCI mapping | Full-depth threat intelligence from architecture alone. Attack path analysis reveals multi-step threats that single-component analysis misses.
F9 | Secure Development Intelligence | Phase 2 | Jul - Nov | 11 | 27 | Unified SAST/SCA/Secrets scanning with AI rule generation, auto-remediation PRs, dev scorecards | Single pane of glass for all code security. Auto-remediation PRs reduce fix time from days to minutes.
F10 | Pipeline Policy-as-Code Enforcement (Advanced) | Phase 2 | Aug - Nov | 10 | 22 | Org-wide CI/CD policy management with auto-correction, SBOM/SLSA/Sigstore enforcement | Supply chain security at scale. Automated enforcement replaces manual audit checklist reviews.
F11 | AI-Driven Inventory & SBOM Platform | Phase 2 | Sep - Dec | 10 | 23 | Application discovery, SBOM generation, dependency health scoring, NVD/OSV correlation | Know what you have before you can secure it. Automated inventory eliminates shadow IT blind spots.
F12 | Advanced VS Code IDE Plugin (V2) | Phase 2 | Sep - Dec | 10 | 21 | 8+ languages, AI remediation, taint tracking, code review assistant, one-click fix | Security intelligence directly in the developer's flow. One-click auto-fix turns security findings into immediate actions.
PHASE 1 MILESTONE TARGETS
Month | Target % | Key Deliverables
Feb | 12% | Research complete; architecture descriptions parser; ASVS mapping engine prototype
Mar | 35% | Core AI engines for requirements + abuse cases + threat modeling working end-to-end
Apr | 58% | JIRA/ADO integrations live; commit scanner real-time; pipeline parser working
May | 82% | All Phase 1 features functional; testing underway; UI polish
Jun | 100% | Phase 1 GA release; VS Code plugin on marketplace; all docs complete
PHASE 2 MILESTONE TARGETS
Month | Target % | Key Deliverables
Jul | 12% | Deep architecture engine; unified SAST engine prototype
Aug | 28% | DFD generation working; SCA integration; org-wide policy management
Sep | 48% | L2 threat modeling; secrets at scale; SBOM generation; extended language support
Oct | 68% | Attack paths; auto-remediation PRs; provenance verification; AI code analysis
Nov | 88% | All features functional; compliance mapping; dashboards; code review assistant
Dec | 100% | Phase 2 GA release; VS Code V2 on marketplace; all docs complete
RISK MITIGATION
Risk |  |  |  | Mitigation
LLM quality/accuracy |  |  |  | Benchmark against OWASP test suites; human-in-the-loop review for critical outputs
JIRA/ADO API changes |  |  |  | Abstract integration layer; versioned API clients; monthly compatibility testing
Phase 1 overrun |  |  |  | F7 can shift 2 weeks into July; buffer built into June
Scope creep |  |  |  | Each feature is self-contained; can defer individual tasks without blocking others
Performance at scale |  |  |  | Commit scanner and SAST engine benchmarked at 1000 repos by Phase 2
SUCCESS METRICS
Metric |  |  |  | Phase 1 Target |  | Phase 2 Target
Features delivered |  |  |  | 7/7 |  | 5/5
Task completion rate |  |  |  | 100% by June 30 |  | 100% by Dec 31
Secret detection recall |  |  |  | >95% |  | >98%
SAST false positive rate |  |  |  | <25% |  | <15%
Threat model generation time |  |  |  | <5 min per architecture |  | <3 min with full depth
JIRA/ADO sync reliability |  |  |  | >99% |  | >99.5%
VS Code analysis latency |  |  |  | <2 seconds |  | <500ms

## Detailed Task List
Phase | Feature ID | Feature Name | Task ID | Task Name | Description | Planned Month | Weight | Owner | Status
F1: Security Requirements Generation
Phase 1 | F1 | Security Requirements Generation | 1.1.1 | OWASP/ASVS Framework Research | Map ASVS 4.0 chapters to actionable requirement categories; document full taxonomy | Feb | 2 |  | Not Started
Phase 1 | F1 | Security Requirements Generation | 1.1.2 | Application Context Schema Design | Input schema: tech stack, data sensitivity, compliance scope, deployment model, user types | Feb | 2 |  | Not Started
Phase 1 | F1 | Security Requirements Generation | 1.1.3 | ASVS Requirement Mapping Engine | Engine mapping ASVS chapters -> controls -> auto-generated requirements per context | Feb-Mar | 3 |  | Not Started
Phase 1 | F1 | Security Requirements Generation | 1.1.4 | AI Requirement Generation Pipeline | LLM pipeline: app context + ASVS mapping -> prioritized security requirements list | Mar | 3 |  | Not Started
Phase 1 | F1 | Security Requirements Generation | 1.1.5 | Requirement Prioritization Engine | Risk-based prioritization (data sensitivity x exposure x compliance) with MoSCoW output | Mar | 2 |  | Not Started
Phase 1 | F1 | Security Requirements Generation | 1.1.6 | JIRA Cloud OAuth Integration | OAuth 2.0 flow; token management; permission scoping; connection health check | Mar-Apr | 3 |  | Not Started
Phase 1 | F1 | Security Requirements Generation | 1.1.7 | JIRA Issue Creation & Sync | Create epics/stories from requirements; bidirectional status sync; field mapping | Apr | 3 |  | Not Started
Phase 1 | F1 | Security Requirements Generation | 1.1.8 | Azure DevOps OAuth Integration | OAuth flow for ADO; PAT fallback; org/project selection UI | Apr | 3 |  | Not Started
Phase 1 | F1 | Security Requirements Generation | 1.1.9 | Azure DevOps Work Item Sync | Create work items; area path mapping; state sync; bulk operations | Apr-May | 3 |  | Not Started
Phase 1 | F1 | Security Requirements Generation | 1.1.10 | Requirement Management UI | Dashboard: generated requirements; edit/approve/reject workflow; bulk actions | Apr-May | 3 |  | Not Started
Phase 1 | F1 | Security Requirements Generation | 1.1.11 | Export Module (PDF/CSV/Markdown) | Export in PDF/CSV/Markdown with traceability metadata | May | 2 |  | Not Started
Phase 1 | F1 | Security Requirements Generation | 1.1.12 | Integration Testing & QA | End-to-end: context input -> generation -> JIRA/ADO sync validation | May | 2 |  | Not Started
Phase 1 | F1 | Security Requirements Generation | 1.1.13 | Documentation & User Guide | User docs, API reference, admin setup guide | May | 1 |  | Not Started
F2: Misuse / Abuse Case Generation
Phase 1 | F2 | Misuse / Abuse Case Generation | 1.2.1 | Abuse Case Taxonomy Research | Map CAPEC + ATT&CK to abuse case templates; define severity model | Feb | 2 |  | Not Started
Phase 1 | F2 | Misuse / Abuse Case Generation | 1.2.2 | Abuse Case Schema & Data Model | Schema: actor profiles, attack steps, preconditions, impact, linked threats | Feb | 2 |  | Not Started
Phase 1 | F2 | Misuse / Abuse Case Generation | 1.2.3 | Architecture Description NLP Parser | Parse free-text architecture into structured components/flows/boundaries | Feb-Mar | 3 |  | Not Started
Phase 1 | F2 | Misuse / Abuse Case Generation | 1.2.4 | Threat Actor Profiling Module | Auto-generate relevant threat actor profiles per application context | Mar | 2 |  | Not Started
Phase 1 | F2 | Misuse / Abuse Case Generation | 1.2.5 | Abuse Case Generation AI Engine | LLM engine: architecture + actor profiles -> structured misuse cases | Mar | 3 |  | Not Started
Phase 1 | F2 | Misuse / Abuse Case Generation | 1.2.6 | Acceptance Criteria Auto-Generation | Generate Given/When/Then acceptance criteria per abuse case | Mar-Apr | 3 |  | Not Started
Phase 1 | F2 | Misuse / Abuse Case Generation | 1.2.7 | Abuse Case Visualization UI | Interactive attack tree / misuse case diagram visualization | Apr | 2 |  | Not Started
Phase 1 | F2 | Misuse / Abuse Case Generation | 1.2.8 | Backlog Export (JIRA/ADO Format) | Export abuse cases as stories/tasks with acceptance criteria | Apr | 2 |  | Not Started
Phase 1 | F2 | Misuse / Abuse Case Generation | 1.2.9 | Testing & QA | Validate against known attack libraries; accuracy benchmarking | Apr | 1 |  | Not Started
F3: Security Acceptance Criteria
Phase 1 | F3 | Security Acceptance Criteria | 1.3.1 | Risk-to-Criteria Mapping Taxonomy | Risk categories -> security control families -> criteria templates | Mar | 2 |  | Not Started
Phase 1 | F3 | Security Acceptance Criteria | 1.3.2 | Threat-to-Criteria Mapping Engine | Auto-map identified threats to testable acceptance criteria | Mar | 3 |  | Not Started
Phase 1 | F3 | Security Acceptance Criteria | 1.3.3 | Criteria Template Library | 200+ pre-built templates by OWASP Top 10 / ASVS / CWE | Mar-Apr | 2 |  | Not Started
Phase 1 | F3 | Security Acceptance Criteria | 1.3.4 | BDD/Gherkin Format Generator | Output in Given/When/Then format for test automation frameworks | Apr | 2 |  | Not Started
Phase 1 | F3 | Security Acceptance Criteria | 1.3.5 | Backlog Integration Module | Attach criteria to JIRA stories / ADO work items | Apr | 3 |  | Not Started
Phase 1 | F3 | Security Acceptance Criteria | 1.3.6 | Criteria Management UI | Browse/filter/edit criteria; approve/reject workflow | Apr-May | 2 |  | Not Started
Phase 1 | F3 | Security Acceptance Criteria | 1.3.7 | Traceability Matrix | Requirement -> Criteria -> Test traceability with coverage metrics | May | 2 |  | Not Started
Phase 1 | F3 | Security Acceptance Criteria | 1.3.8 | Testing & QA | Validate criteria quality and mapping accuracy | May | 1 |  | Not Started
F4: AI-Assisted Threat Modeling (L0 & L1)
Phase 1 | F4 | AI-Assisted Threat Modeling (L0 & L1) | 1.4.1 | Architecture Input Design | Text descriptions + diagram upload (image-to-components via vision) | Feb | 2 |  | Not Started
Phase 1 | F4 | AI-Assisted Threat Modeling (L0 & L1) | 1.4.2 | Architecture NLP Parser & Component Extraction | Extract components/services/data stores/external systems | Feb-Mar | 3 |  | Not Started
Phase 1 | F4 | AI-Assisted Threat Modeling (L0 & L1) | 1.4.3 | Trust Boundary Auto-Identification | Identify trust boundaries: network/process/privilege | Mar | 2 |  | Not Started
Phase 1 | F4 | AI-Assisted Threat Modeling (L0 & L1) | 1.4.4 | L0 Threat Model Generator | System-level threats and high-level attack surfaces | Mar-Apr | 3 |  | Not Started
Phase 1 | F4 | AI-Assisted Threat Modeling (L0 & L1) | 1.4.5 | L1 Threat Model Generator | Per-component STRIDE analysis with data flow context | Apr | 3 |  | Not Started
Phase 1 | F4 | AI-Assisted Threat Modeling (L0 & L1) | 1.4.6 | STRIDE Mapping Engine | Automated STRIDE categorization with confidence scoring | Apr-May | 3 |  | Not Started
Phase 1 | F4 | AI-Assisted Threat Modeling (L0 & L1) | 1.4.7 | Mitigation Recommendation Engine | AI-generated mitigations mapped to NIST/OWASP controls | May | 3 |  | Not Started
Phase 1 | F4 | AI-Assisted Threat Modeling (L0 & L1) | 1.4.8 | Threat Model Visualization | Interactive DFD with threat overlays; Eraser.io integration | May | 2 |  | Not Started
Phase 1 | F4 | AI-Assisted Threat Modeling (L0 & L1) | 1.4.9 | Report Generation (PDF) | Executive summary + detailed report with risk matrix | May-Jun | 2 |  | Not Started
Phase 1 | F4 | AI-Assisted Threat Modeling (L0 & L1) | 1.4.10 | Threat Model Versioning & Comparison | Version history with diff: new/removed/changed threats | Jun | 2 |  | Not Started
Phase 1 | F4 | AI-Assisted Threat Modeling (L0 & L1) | 1.4.11 | Integration Testing & QA | Test against reference architectures | Jun | 1 |  | Not Started
F5: Commit Scanner
Phase 1 | F5 | Commit Scanner | 1.5.1 | Secret Detection Pattern Library | 300+ patterns for API keys/tokens/passwords across 50+ services | Mar | 2 |  | Not Started
Phase 1 | F5 | Commit Scanner | 1.5.2 | Entropy + Regex Detection Engine | Hybrid: regex patterns + Shannon entropy for unknown formats | Mar | 3 |  | Not Started
Phase 1 | F5 | Commit Scanner | 1.5.3 | GitHub Webhook Real-time Scanning | GitHub App webhook push events; real-time diff scanning | Mar-Apr | 3 |  | Not Started
Phase 1 | F5 | Commit Scanner | 1.5.4 | GitLab Webhook Integration | GitLab push event webhook with real-time scanning | Apr | 2 |  | Not Started
Phase 1 | F5 | Commit Scanner | 1.5.5 | Historical Full-Repo Scan | Scan entire git history; progress tracking for large repos | Apr | 3 |  | Not Started
Phase 1 | F5 | Commit Scanner | 1.5.6 | False Positive Reduction Engine | Context-aware filtering: test files/example configs/docs | Apr-May | 2 |  | Not Started
Phase 1 | F5 | Commit Scanner | 1.5.7 | Remediation Guidance Generator | Per-secret-type rotation instructions + prevention config | May | 2 |  | Not Started
Phase 1 | F5 | Commit Scanner | 1.5.8 | Alerting System (Email/Slack/Teams) | Configurable alert channels with severity-based routing | May | 2 |  | Not Started
Phase 1 | F5 | Commit Scanner | 1.5.9 | Scanner Dashboard & Metrics | Scan history, secret trends, SLA tracking | May | 2 |  | Not Started
Phase 1 | F5 | Commit Scanner | 1.5.10 | Testing & QA | Test against known secret corpuses; FP rate benchmarking | May | 1 |  | Not Started
F6: Pipeline Policy-as-Code Validator
Phase 1 | F6 | Pipeline Policy-as-Code Validator | 1.6.1 | Policy Definition Schema (YAML) | YAML-based policy language for AppSec requirements | Apr | 2 |  | Not Started
Phase 1 | F6 | Pipeline Policy-as-Code Validator | 1.6.2 | GitHub Actions Pipeline Parser | Parse YAML; extract steps/actions/security invocations | Apr | 3 |  | Not Started
Phase 1 | F6 | Pipeline Policy-as-Code Validator | 1.6.3 | Jenkins Pipeline Parser | Parse Jenkinsfile (declarative + scripted) | Apr-May | 2 |  | Not Started
Phase 1 | F6 | Pipeline Policy-as-Code Validator | 1.6.4 | GitLab CI Pipeline Parser | Parse .gitlab-ci.yml | May | 2 |  | Not Started
Phase 1 | F6 | Pipeline Policy-as-Code Validator | 1.6.5 | Azure Pipelines Parser | Parse azure-pipelines.yml | May | 2 |  | Not Started
Phase 1 | F6 | Pipeline Policy-as-Code Validator | 1.6.6 | AppSec Control Validation Rules | Rule engine: SAST? SCA? Secrets? DAST? Image scan? | May | 3 |  | Not Started
Phase 1 | F6 | Pipeline Policy-as-Code Validator | 1.6.7 | Compliance Checker | Pass/fail/warning per control against policy | May-Jun | 3 |  | Not Started
Phase 1 | F6 | Pipeline Policy-as-Code Validator | 1.6.8 | AI Corrective Step Suggestions | LLM-generated pipeline fix suggestions with diff preview | Jun | 2 |  | Not Started
Phase 1 | F6 | Pipeline Policy-as-Code Validator | 1.6.9 | Policy Management UI | Create/edit/version policies; assign to repos | Jun | 2 |  | Not Started
Phase 1 | F6 | Pipeline Policy-as-Code Validator | 1.6.10 | Compliance Dashboard & Reporting | Org-wide compliance overview; trend charts | Jun | 2 |  | Not Started
Phase 1 | F6 | Pipeline Policy-as-Code Validator | 1.6.11 | Testing & QA | Test against real-world open-source pipelines | Jun | 1 |  | Not Started
F7: VS Code Plugin (Initial Version)
Phase 1 | F7 | VS Code Plugin (Initial Version) | 1.7.1 | Extension Scaffolding & Architecture | Project setup; activation events; command palette | Apr | 2 |  | Not Started
Phase 1 | F7 | VS Code Plugin (Initial Version) | 1.7.2 | Python Language Support | SQL injection / command injection / crypto misuse analysis | Apr-May | 3 |  | Not Started
Phase 1 | F7 | VS Code Plugin (Initial Version) | 1.7.3 | JavaScript/TypeScript Support | XSS / prototype pollution / insecure dependency analysis | May | 3 |  | Not Started
Phase 1 | F7 | VS Code Plugin (Initial Version) | 1.7.4 | Inline Security Hint Engine | VS Code Diagnostics API; squiggly underlines + hover | May | 3 |  | Not Started
Phase 1 | F7 | VS Code Plugin (Initial Version) | 1.7.5 | Basic Remediation Suggestions | CodeAction provider with quick-fix suggestions | May-Jun | 2 |  | Not Started
Phase 1 | F7 | VS Code Plugin (Initial Version) | 1.7.6 | Settings & Configuration | Severity thresholds; language toggles; API connection | Jun | 1 |  | Not Started
Phase 1 | F7 | VS Code Plugin (Initial Version) | 1.7.7 | Backend Auth & Connection | Token auth to backend; connection health indicator | Jun | 2 |  | Not Started
Phase 1 | F7 | VS Code Plugin (Initial Version) | 1.7.8 | Marketplace Packaging | .vsix packaging; listing; icon/README/changelog | Jun | 1 |  | Not Started
Phase 1 | F7 | VS Code Plugin (Initial Version) | 1.7.9 | Beta Testing & Feedback | Beta with 10+ devs; structured feedback | Jun | 2 |  | Not Started
Phase 1 | F7 | VS Code Plugin (Initial Version) | 1.7.10 | Documentation & Quick Start | Getting started; feature walkthrough; FAQ | Jun | 1 |  | Not Started
F8: Full AI Threat Modeling
Phase 2 | F8 | Full AI Threat Modeling | 2.1.1 | Deep Architecture Analysis Engine | Multi-tier / microservices / serverless architecture understanding | Jul | 3 |  | Not Started
Phase 2 | F8 | Full AI Threat Modeling | 2.1.2 | Automated Dataflow Modeling | Auto-generate DFDs from architecture descriptions + code analysis | Jul-Aug | 3 |  | Not Started
Phase 2 | F8 | Full AI Threat Modeling | 2.1.3 | Data Classification & Sensitivity | Auto-classify data types (PII/PHI/financial/credentials) | Aug | 2 |  | Not Started
Phase 2 | F8 | Full AI Threat Modeling | 2.1.4 | Design Flaw Detection Engine | Identify anti-patterns: missing auth / unencrypted channels / SPOFs | Aug-Sep | 3 |  | Not Started
Phase 2 | F8 | Full AI Threat Modeling | 2.1.5 | Layered STRIDE Mapping (L0/L1/L2) | Three-level STRIDE with inheritance and rollup | Sep | 3 |  | Not Started
Phase 2 | F8 | Full AI Threat Modeling | 2.1.6 | L2 Threat Model (Data-Flow Level) | Granular threats per data flow: injection/auth bypass/leakage | Sep | 3 |  | Not Started
Phase 2 | F8 | Full AI Threat Modeling | 2.1.7 | Threat Chaining & Attack Paths | Multi-step attack path identification; kill chains | Sep-Oct | 3 |  | Not Started
Phase 2 | F8 | Full AI Threat Modeling | 2.1.8 | Control Gap Analysis Engine | Map controls to threats; identify gaps; prioritize remediation | Oct | 2 |  | Not Started
Phase 2 | F8 | Full AI Threat Modeling | 2.1.9 | Interactive Threat Model Editor | Drag-and-drop DFD with real-time threat re-analysis | Oct | 3 |  | Not Started
Phase 2 | F8 | Full AI Threat Modeling | 2.1.10 | Compliance Mapping (NIST/ISO/PCI) | Map to NIST 800-53 / ISO 27001 / PCI DSS / SOC 2 | Oct-Nov | 2 |  | Not Started
Phase 2 | F8 | Full AI Threat Modeling | 2.1.11 | Threat Model Diff & Change Impact | Compare versions; highlight new attack surfaces | Nov | 2 |  | Not Started
Phase 2 | F8 | Full AI Threat Modeling | 2.1.12 | Integration Testing & QA | Benchmark against OWASP reference architectures | Nov | 1 |  | Not Started
F9: Secure Development Intelligence
Phase 2 | F9 | Secure Development Intelligence | 2.2.1 | Unified Multi-Language SAST Engine | Support 10+ languages with unified finding format; custom rule SDK | Jul-Aug | 3 |  | Not Started
Phase 2 | F9 | Secure Development Intelligence | 2.2.2 | SCA Scanner with Vuln Correlation | Dependency scanning with NVD/OSV/GitHub Advisory; reachability | Aug | 3 |  | Not Started
Phase 2 | F9 | Secure Development Intelligence | 2.2.3 | Enterprise Secrets Scanning | Scale to 1000+ repos; incremental scanning; pre-commit hooks | Aug-Sep | 3 |  | Not Started
Phase 2 | F9 | Secure Development Intelligence | 2.2.4 | AI Custom Rule Generation | Generate SAST rules from CVE reports | Sep | 3 |  | Not Started
Phase 2 | F9 | Secure Development Intelligence | 2.2.5 | Commit Scanning at Scale | Parallel commit analysis; queue management; rate limiting | Sep-Oct | 3 |  | Not Started
Phase 2 | F9 | Secure Development Intelligence | 2.2.6 | Automated Remediation PR Generation | Auto-generate fix PRs with test validation | Oct | 3 |  | Not Started
Phase 2 | F9 | Secure Development Intelligence | 2.2.7 | Developer Security Scorecard | Per-developer metrics: fix rate / introduction rate / response time | Oct-Nov | 2 |  | Not Started
Phase 2 | F9 | Secure Development Intelligence | 2.2.8 | Security Metrics & Trend Dashboards | MTTR / vulnerability density / fix velocity trending | Nov | 2 |  | Not Started
Phase 2 | F9 | Secure Development Intelligence | 2.2.9 | Scan Orchestration & Scheduling | Cron/event-driven scheduling; priority queues | Nov | 2 |  | Not Started
Phase 2 | F9 | Secure Development Intelligence | 2.2.10 | Finding Dedup & Correlation | Cross-scanner deduplication; correlate SAST+SCA+secrets | Nov | 2 |  | Not Started
Phase 2 | F9 | Secure Development Intelligence | 2.2.11 | Testing & QA | OWASP Benchmark; FP rate < 15% target | Nov | 1 |  | Not Started
F10: Pipeline Policy-as-Code Enforcement (Advanced)
Phase 2 | F10 | Pipeline Policy-as-Code Enforcement (Advanced) | 2.3.1 | Org-Wide Policy Management | Hierarchical policies: org -> team -> repo with override/merge | Aug | 3 |  | Not Started
Phase 2 | F10 | Pipeline Policy-as-Code Enforcement (Advanced) | 2.3.2 | Pipeline Auto-Correction Engine | AI-generated pipeline patches; PR-based workflow | Aug-Sep | 3 |  | Not Started
Phase 2 | F10 | Pipeline Policy-as-Code Enforcement (Advanced) | 2.3.3 | SBOM Generation Enforcement | Require CycloneDX/SPDX SBOM; validate completeness | Sep | 2 |  | Not Started
Phase 2 | F10 | Pipeline Policy-as-Code Enforcement (Advanced) | 2.3.4 | Provenance Verification Engine | SLSA provenance verification; build attestation | Sep-Oct | 3 |  | Not Started
Phase 2 | F10 | Pipeline Policy-as-Code Enforcement (Advanced) | 2.3.5 | Artifact Signature Enforcement | Require Sigstore/Cosign signatures | Oct | 2 |  | Not Started
Phase 2 | F10 | Pipeline Policy-as-Code Enforcement (Advanced) | 2.3.6 | Policy Violation Alerting | Real-time alerts; escalation chains; SLA tracking | Oct | 2 |  | Not Started
Phase 2 | F10 | Pipeline Policy-as-Code Enforcement (Advanced) | 2.3.7 | Compliance Reporting Dashboard | SOC 2 / ISO / NIST evidence generation | Oct-Nov | 2 |  | Not Started
Phase 2 | F10 | Pipeline Policy-as-Code Enforcement (Advanced) | 2.3.8 | Policy Versioning & Rollback | Git-backed versioning; rollback; audit log | Nov | 2 |  | Not Started
Phase 2 | F10 | Pipeline Policy-as-Code Enforcement (Advanced) | 2.3.9 | Exception Management Workflow | Request/approve/expire exception workflow | Nov | 2 |  | Not Started
Phase 2 | F10 | Pipeline Policy-as-Code Enforcement (Advanced) | 2.3.10 | Testing & QA | Test across 100+ pipeline configurations | Nov | 1 |  | Not Started
F11: AI-Driven Inventory & SBOM Platform
Phase 2 | F11 | AI-Driven Inventory & SBOM Platform | 2.4.1 | Agent-Based Application Discovery | Scan org repos for tech stacks / frameworks / services | Sep | 3 |  | Not Started
Phase 2 | F11 | AI-Driven Inventory & SBOM Platform | 2.4.2 | Automated SBOM Generation | CycloneDX + SPDX from source / manifests / containers | Sep-Oct | 3 |  | Not Started
Phase 2 | F11 | AI-Driven Inventory & SBOM Platform | 2.4.3 | Dependency Health Scoring | Score: maintenance / vulns / license risk / age / popularity | Oct | 3 |  | Not Started
Phase 2 | F11 | AI-Driven Inventory & SBOM Platform | 2.4.4 | Vulnerability Correlation Engine | Cross-reference NVD / OSV / GitHub Advisory / vendor feeds | Oct-Nov | 3 |  | Not Started
Phase 2 | F11 | AI-Driven Inventory & SBOM Platform | 2.4.5 | License Tracking & Compliance | Detect license types; flag copyleft; compliance reports | Nov | 2 |  | Not Started
Phase 2 | F11 | AI-Driven Inventory & SBOM Platform | 2.4.6 | Dependency Graph Visualization | Interactive tree with vuln/license overlays | Nov | 2 |  | Not Started
Phase 2 | F11 | AI-Driven Inventory & SBOM Platform | 2.4.7 | Risk-Based Vuln Prioritization | EPSS + reachability + exploit maturity scoring | Nov-Dec | 2 |  | Not Started
Phase 2 | F11 | AI-Driven Inventory & SBOM Platform | 2.4.8 | Inventory Management Dashboard | Unified catalog: stack / owner / risk / SBOM freshness | Dec | 2 |  | Not Started
Phase 2 | F11 | AI-Driven Inventory & SBOM Platform | 2.4.9 | Automated Update Recommendations | AI-suggested updates with breaking change assessment | Dec | 2 |  | Not Started
Phase 2 | F11 | AI-Driven Inventory & SBOM Platform | 2.4.10 | Testing & QA | Validate against known vulnerable dependency sets | Dec | 1 |  | Not Started
F12: Advanced VS Code IDE Plugin (V2)
Phase 2 | F12 | Advanced VS Code IDE Plugin (V2) | 2.5.1 | Extended Language Support | Java / Go / C# / Ruby / PHP / Kotlin analysis | Sep-Oct | 3 |  | Not Started
Phase 2 | F12 | Advanced VS Code IDE Plugin (V2) | 2.5.2 | Real-Time AI Remediation Engine | Context-aware fix generation with codebase understanding | Oct | 3 |  | Not Started
Phase 2 | F12 | Advanced VS Code IDE Plugin (V2) | 2.5.3 | Intelligent Code Analysis | Semantic taint tracking / data flow in IDE | Oct-Nov | 3 |  | Not Started
Phase 2 | F12 | Advanced VS Code IDE Plugin (V2) | 2.5.4 | Risk Profile Integration | Project risk score / findings in sidebar | Nov | 2 |  | Not Started
Phase 2 | F12 | Advanced VS Code IDE Plugin (V2) | 2.5.5 | Inline Threat Context Overlay | Threat model -> code mapping in editor | Nov | 2 |  | Not Started
Phase 2 | F12 | Advanced VS Code IDE Plugin (V2) | 2.5.6 | AI Code Review Assistant | Pre-commit security review; risk summary | Nov-Dec | 3 |  | Not Started
Phase 2 | F12 | Advanced VS Code IDE Plugin (V2) | 2.5.7 | Team Security Metrics Widget | Team fix rate / open vulns / score panel | Dec | 1 |  | Not Started
Phase 2 | F12 | Advanced VS Code IDE Plugin (V2) | 2.5.8 | One-Click Auto-Fix | Apply AI fixes with diff preview | Dec | 2 |  | Not Started
Phase 2 | F12 | Advanced VS Code IDE Plugin (V2) | 2.5.9 | Marketplace V2 Publishing | Listing update; V1 migration guide | Dec | 1 |  | Not Started
Phase 2 | F12 | Advanced VS Code IDE Plugin (V2) | 2.5.10 | Testing & QA | Cross-language; <500ms target | Dec | 1 |  | Not Started

## F1
F1: Security Requirements Generation
Automatically generate OWASP ASVS-aligned security requirements based on application context (tech stack, data sensitivity, compliance scope) and push them directly into JIRA or Azure DevOps backlogs.
Value: Eliminates the manual effort of writing security requirements for each project. Ensures consistent coverage against OWASP ASVS 4.0. Cuts requirements phase from 2 weeks to 2 hours.
Phase | Phase 1 | Timeline | Feb - May | Tasks | 13 | Total Weight | 32 | Owner | ___________
Task ID | Task Name | Description | Month | Weight | Owner | Status | Completion %
1.1.1 | OWASP/ASVS Framework Research | Map ASVS 4.0 chapters to actionable requirement categories; document full taxonomy | Feb | 2 |  | Not Started | 0
1.1.2 | Application Context Schema Design | Input schema: tech stack, data sensitivity, compliance scope, deployment model, user types | Feb | 2 |  | Not Started | 0
1.1.3 | ASVS Requirement Mapping Engine | Engine mapping ASVS chapters -> controls -> auto-generated requirements per context | Feb-Mar | 3 |  | Not Started | 0
1.1.4 | AI Requirement Generation Pipeline | LLM pipeline: app context + ASVS mapping -> prioritized security requirements list | Mar | 3 |  | Not Started | 0
1.1.5 | Requirement Prioritization Engine | Risk-based prioritization (data sensitivity x exposure x compliance) with MoSCoW output | Mar | 2 |  | Not Started | 0
1.1.6 | JIRA Cloud OAuth Integration | OAuth 2.0 flow; token management; permission scoping; connection health check | Mar-Apr | 3 |  | Not Started | 0
1.1.7 | JIRA Issue Creation & Sync | Create epics/stories from requirements; bidirectional status sync; field mapping | Apr | 3 |  | Not Started | 0
1.1.8 | Azure DevOps OAuth Integration | OAuth flow for ADO; PAT fallback; org/project selection UI | Apr | 3 |  | Not Started | 0
1.1.9 | Azure DevOps Work Item Sync | Create work items; area path mapping; state sync; bulk operations | Apr-May | 3 |  | Not Started | 0
1.1.10 | Requirement Management UI | Dashboard: generated requirements; edit/approve/reject workflow; bulk actions | Apr-May | 3 |  | Not Started | 0
1.1.11 | Export Module (PDF/CSV/Markdown) | Export in PDF/CSV/Markdown with traceability metadata | May | 2 |  | Not Started | 0
1.1.12 | Integration Testing & QA | End-to-end: context input -> generation -> JIRA/ADO sync validation | May | 2 |  | Not Started | 0
1.1.13 | Documentation & User Guide | User docs, API reference, admin setup guide | May | 1 |  | Not Started | 0
TOTAL |  |  |  | 32 |  |  | Weighted Avg

## F2
F2: Misuse / Abuse Case Generation
Generate structured misuse and abuse cases from architecture descriptions, complete with threat actor profiles, attack steps, and testable acceptance criteria.
Value: Bridges the gap between threat modeling and development. Developers get concrete abuse scenarios instead of abstract threat lists.
Phase | Phase 1 | Timeline | Feb - Apr | Tasks | 9 | Total Weight | 20 | Owner | ___________
Task ID | Task Name | Description | Month | Weight | Owner | Status | Completion %
1.2.1 | Abuse Case Taxonomy Research | Map CAPEC + ATT&CK to abuse case templates; define severity model | Feb | 2 |  | Not Started | 0
1.2.2 | Abuse Case Schema & Data Model | Schema: actor profiles, attack steps, preconditions, impact, linked threats | Feb | 2 |  | Not Started | 0
1.2.3 | Architecture Description NLP Parser | Parse free-text architecture into structured components/flows/boundaries | Feb-Mar | 3 |  | Not Started | 0
1.2.4 | Threat Actor Profiling Module | Auto-generate relevant threat actor profiles per application context | Mar | 2 |  | Not Started | 0
1.2.5 | Abuse Case Generation AI Engine | LLM engine: architecture + actor profiles -> structured misuse cases | Mar | 3 |  | Not Started | 0
1.2.6 | Acceptance Criteria Auto-Generation | Generate Given/When/Then acceptance criteria per abuse case | Mar-Apr | 3 |  | Not Started | 0
1.2.7 | Abuse Case Visualization UI | Interactive attack tree / misuse case diagram visualization | Apr | 2 |  | Not Started | 0
1.2.8 | Backlog Export (JIRA/ADO Format) | Export abuse cases as stories/tasks with acceptance criteria | Apr | 2 |  | Not Started | 0
1.2.9 | Testing & QA | Validate against known attack libraries; accuracy benchmarking | Apr | 1 |  | Not Started | 0
TOTAL |  |  |  | 20 |  |  | Weighted Avg

## F3
F3: Security Acceptance Criteria
Create security acceptance criteria mapped to identified risks and threats, in BDD/Gherkin format, ready for backlog integration.
Value: Makes security testable and trackable. QA teams get concrete criteria. Completion can be measured like any other user story.
Phase | Phase 1 | Timeline | Mar - May | Tasks | 8 | Total Weight | 17 | Owner | ___________
Task ID | Task Name | Description | Month | Weight | Owner | Status | Completion %
1.3.1 | Risk-to-Criteria Mapping Taxonomy | Risk categories -> security control families -> criteria templates | Mar | 2 |  | Not Started | 0
1.3.2 | Threat-to-Criteria Mapping Engine | Auto-map identified threats to testable acceptance criteria | Mar | 3 |  | Not Started | 0
1.3.3 | Criteria Template Library | 200+ pre-built templates by OWASP Top 10 / ASVS / CWE | Mar-Apr | 2 |  | Not Started | 0
1.3.4 | BDD/Gherkin Format Generator | Output in Given/When/Then format for test automation frameworks | Apr | 2 |  | Not Started | 0
1.3.5 | Backlog Integration Module | Attach criteria to JIRA stories / ADO work items | Apr | 3 |  | Not Started | 0
1.3.6 | Criteria Management UI | Browse/filter/edit criteria; approve/reject workflow | Apr-May | 2 |  | Not Started | 0
1.3.7 | Traceability Matrix | Requirement -> Criteria -> Test traceability with coverage metrics | May | 2 |  | Not Started | 0
1.3.8 | Testing & QA | Validate criteria quality and mapping accuracy | May | 1 |  | Not Started | 0
TOTAL |  |  |  | 17 |  |  | Weighted Avg

## F4
F4: AI-Assisted Threat Modeling (L0 & L1)
Use only architecture descriptions to auto-generate high-level (L0: system) and detailed (L1: component) threat models with STRIDE categorization and mitigation recommendations.
Value: Removes the need for security architects to manually create threat models. Any development team can generate a threat model in minutes instead of days.
Phase | Phase 1 | Timeline | Feb - Jun | Tasks | 11 | Total Weight | 26 | Owner | ___________
Task ID | Task Name | Description | Month | Weight | Owner | Status | Completion %
1.4.1 | Architecture Input Design | Text descriptions + diagram upload (image-to-components via vision) | Feb | 2 |  | Not Started | 0
1.4.2 | Architecture NLP Parser & Component Extraction | Extract components/services/data stores/external systems | Feb-Mar | 3 |  | Not Started | 0
1.4.3 | Trust Boundary Auto-Identification | Identify trust boundaries: network/process/privilege | Mar | 2 |  | Not Started | 0
1.4.4 | L0 Threat Model Generator | System-level threats and high-level attack surfaces | Mar-Apr | 3 |  | Not Started | 0
1.4.5 | L1 Threat Model Generator | Per-component STRIDE analysis with data flow context | Apr | 3 |  | Not Started | 0
1.4.6 | STRIDE Mapping Engine | Automated STRIDE categorization with confidence scoring | Apr-May | 3 |  | Not Started | 0
1.4.7 | Mitigation Recommendation Engine | AI-generated mitigations mapped to NIST/OWASP controls | May | 3 |  | Not Started | 0
1.4.8 | Threat Model Visualization | Interactive DFD with threat overlays; Eraser.io integration | May | 2 |  | Not Started | 0
1.4.9 | Report Generation (PDF) | Executive summary + detailed report with risk matrix | May-Jun | 2 |  | Not Started | 0
1.4.10 | Threat Model Versioning & Comparison | Version history with diff: new/removed/changed threats | Jun | 2 |  | Not Started | 0
1.4.11 | Integration Testing & QA | Test against reference architectures | Jun | 1 |  | Not Started | 0
TOTAL |  |  |  | 26 |  |  | Weighted Avg

## F5
F5: Commit Scanner
Detect secrets and sensitive information in developer commits across GitHub and GitLab, with real-time alerting and remediation guidance.
Value: Prevents credential leaks before they reach production. Reduces secret exposure window from days to seconds.
Phase | Phase 1 | Timeline | Mar - May | Tasks | 10 | Total Weight | 22 | Owner | ___________
Task ID | Task Name | Description | Month | Weight | Owner | Status | Completion %
1.5.1 | Secret Detection Pattern Library | 300+ patterns for API keys/tokens/passwords across 50+ services | Mar | 2 |  | Not Started | 0
1.5.2 | Entropy + Regex Detection Engine | Hybrid: regex patterns + Shannon entropy for unknown formats | Mar | 3 |  | Not Started | 0
1.5.3 | GitHub Webhook Real-time Scanning | GitHub App webhook push events; real-time diff scanning | Mar-Apr | 3 |  | Not Started | 0
1.5.4 | GitLab Webhook Integration | GitLab push event webhook with real-time scanning | Apr | 2 |  | Not Started | 0
1.5.5 | Historical Full-Repo Scan | Scan entire git history; progress tracking for large repos | Apr | 3 |  | Not Started | 0
1.5.6 | False Positive Reduction Engine | Context-aware filtering: test files/example configs/docs | Apr-May | 2 |  | Not Started | 0
1.5.7 | Remediation Guidance Generator | Per-secret-type rotation instructions + prevention config | May | 2 |  | Not Started | 0
1.5.8 | Alerting System (Email/Slack/Teams) | Configurable alert channels with severity-based routing | May | 2 |  | Not Started | 0
1.5.9 | Scanner Dashboard & Metrics | Scan history, secret trends, SLA tracking | May | 2 |  | Not Started | 0
1.5.10 | Testing & QA | Test against known secret corpuses; FP rate benchmarking | May | 1 |  | Not Started | 0
TOTAL |  |  |  | 22 |  |  | Weighted Avg

## F6
F6: Pipeline Policy-as-Code Validator
Validate CI/CD pipelines against required AppSec controls and suggest corrective steps. Supports GitHub Actions, Jenkins, GitLab CI, and Azure Pipelines.
Value: Ensures every pipeline has required security gates. Catches missing SAST/SCA/DAST steps before code ships.
Phase | Phase 1 | Timeline | Apr - Jun | Tasks | 11 | Total Weight | 24 | Owner | ___________
Task ID | Task Name | Description | Month | Weight | Owner | Status | Completion %
1.6.1 | Policy Definition Schema (YAML) | YAML-based policy language for AppSec requirements | Apr | 2 |  | Not Started | 0
1.6.2 | GitHub Actions Pipeline Parser | Parse YAML; extract steps/actions/security invocations | Apr | 3 |  | Not Started | 0
1.6.3 | Jenkins Pipeline Parser | Parse Jenkinsfile (declarative + scripted) | Apr-May | 2 |  | Not Started | 0
1.6.4 | GitLab CI Pipeline Parser | Parse .gitlab-ci.yml | May | 2 |  | Not Started | 0
1.6.5 | Azure Pipelines Parser | Parse azure-pipelines.yml | May | 2 |  | Not Started | 0
1.6.6 | AppSec Control Validation Rules | Rule engine: SAST? SCA? Secrets? DAST? Image scan? | May | 3 |  | Not Started | 0
1.6.7 | Compliance Checker | Pass/fail/warning per control against policy | May-Jun | 3 |  | Not Started | 0
1.6.8 | AI Corrective Step Suggestions | LLM-generated pipeline fix suggestions with diff preview | Jun | 2 |  | Not Started | 0
1.6.9 | Policy Management UI | Create/edit/version policies; assign to repos | Jun | 2 |  | Not Started | 0
1.6.10 | Compliance Dashboard & Reporting | Org-wide compliance overview; trend charts | Jun | 2 |  | Not Started | 0
1.6.11 | Testing & QA | Test against real-world open-source pipelines | Jun | 1 |  | Not Started | 0
TOTAL |  |  |  | 24 |  |  | Weighted Avg

## F7
F7: VS Code Plugin (Initial Version)
IDE support for Python and JavaScript/TypeScript with inline security hints and basic remediation.
Value: Security feedback at the point of code creation. Developers see issues before commit, not after a scan.
Phase | Phase 1 | Timeline | Apr - Jun | Tasks | 10 | Total Weight | 20 | Owner | ___________
Task ID | Task Name | Description | Month | Weight | Owner | Status | Completion %
1.7.1 | Extension Scaffolding & Architecture | Project setup; activation events; command palette | Apr | 2 |  | Not Started | 0
1.7.2 | Python Language Support | SQL injection / command injection / crypto misuse analysis | Apr-May | 3 |  | Not Started | 0
1.7.3 | JavaScript/TypeScript Support | XSS / prototype pollution / insecure dependency analysis | May | 3 |  | Not Started | 0
1.7.4 | Inline Security Hint Engine | VS Code Diagnostics API; squiggly underlines + hover | May | 3 |  | Not Started | 0
1.7.5 | Basic Remediation Suggestions | CodeAction provider with quick-fix suggestions | May-Jun | 2 |  | Not Started | 0
1.7.6 | Settings & Configuration | Severity thresholds; language toggles; API connection | Jun | 1 |  | Not Started | 0
1.7.7 | Backend Auth & Connection | Token auth to backend; connection health indicator | Jun | 2 |  | Not Started | 0
1.7.8 | Marketplace Packaging | .vsix packaging; listing; icon/README/changelog | Jun | 1 |  | Not Started | 0
1.7.9 | Beta Testing & Feedback | Beta with 10+ devs; structured feedback | Jun | 2 |  | Not Started | 0
1.7.10 | Documentation & Quick Start | Getting started; feature walkthrough; FAQ | Jun | 1 |  | Not Started | 0
TOTAL |  |  |  | 20 |  |  | Weighted Avg

## F8
F8: Full AI Threat Modeling
Deep architecture analysis, automated dataflow modeling, design flaw detection, layered STRIDE mapping (L0/L1/L2), and attack path analysis.
Value: Full-depth threat intelligence from architecture alone. Attack path analysis reveals multi-step threats that single-component analysis misses.
Phase | Phase 2 | Timeline | Jul - Nov | Tasks | 12 | Total Weight | 30 | Owner | ___________
Task ID | Task Name | Description | Month | Weight | Owner | Status | Completion %
2.1.1 | Deep Architecture Analysis Engine | Multi-tier / microservices / serverless architecture understanding | Jul | 3 |  | Not Started | 0
2.1.2 | Automated Dataflow Modeling | Auto-generate DFDs from architecture descriptions + code analysis | Jul-Aug | 3 |  | Not Started | 0
2.1.3 | Data Classification & Sensitivity | Auto-classify data types (PII/PHI/financial/credentials) | Aug | 2 |  | Not Started | 0
2.1.4 | Design Flaw Detection Engine | Identify anti-patterns: missing auth / unencrypted channels / SPOFs | Aug-Sep | 3 |  | Not Started | 0
2.1.5 | Layered STRIDE Mapping (L0/L1/L2) | Three-level STRIDE with inheritance and rollup | Sep | 3 |  | Not Started | 0
2.1.6 | L2 Threat Model (Data-Flow Level) | Granular threats per data flow: injection/auth bypass/leakage | Sep | 3 |  | Not Started | 0
2.1.7 | Threat Chaining & Attack Paths | Multi-step attack path identification; kill chains | Sep-Oct | 3 |  | Not Started | 0
2.1.8 | Control Gap Analysis Engine | Map controls to threats; identify gaps; prioritize remediation | Oct | 2 |  | Not Started | 0
2.1.9 | Interactive Threat Model Editor | Drag-and-drop DFD with real-time threat re-analysis | Oct | 3 |  | Not Started | 0
2.1.10 | Compliance Mapping (NIST/ISO/PCI) | Map to NIST 800-53 / ISO 27001 / PCI DSS / SOC 2 | Oct-Nov | 2 |  | Not Started | 0
2.1.11 | Threat Model Diff & Change Impact | Compare versions; highlight new attack surfaces | Nov | 2 |  | Not Started | 0
2.1.12 | Integration Testing & QA | Benchmark against OWASP reference architectures | Nov | 1 |  | Not Started | 0
TOTAL |  |  |  | 30 |  |  | Weighted Avg

## F9
F9: Secure Development Intelligence
Unified SAST/SCA/Secrets scanning, AI rule generation, commit scanning at scale, automated remediation PRs, and developer security scorecards.
Value: Single pane of glass for all code security. Auto-remediation PRs reduce fix time from days to minutes.
Phase | Phase 2 | Timeline | Jul - Nov | Tasks | 11 | Total Weight | 27 | Owner | ___________
Task ID | Task Name | Description | Month | Weight | Owner | Status | Completion %
2.2.1 | Unified Multi-Language SAST Engine | Support 10+ languages with unified finding format; custom rule SDK | Jul-Aug | 3 |  | Not Started | 0
2.2.2 | SCA Scanner with Vuln Correlation | Dependency scanning with NVD/OSV/GitHub Advisory; reachability | Aug | 3 |  | Not Started | 0
2.2.3 | Enterprise Secrets Scanning | Scale to 1000+ repos; incremental scanning; pre-commit hooks | Aug-Sep | 3 |  | Not Started | 0
2.2.4 | AI Custom Rule Generation | Generate SAST rules from CVE reports | Sep | 3 |  | Not Started | 0
2.2.5 | Commit Scanning at Scale | Parallel commit analysis; queue management; rate limiting | Sep-Oct | 3 |  | Not Started | 0
2.2.6 | Automated Remediation PR Generation | Auto-generate fix PRs with test validation | Oct | 3 |  | Not Started | 0
2.2.7 | Developer Security Scorecard | Per-developer metrics: fix rate / introduction rate / response time | Oct-Nov | 2 |  | Not Started | 0
2.2.8 | Security Metrics & Trend Dashboards | MTTR / vulnerability density / fix velocity trending | Nov | 2 |  | Not Started | 0
2.2.9 | Scan Orchestration & Scheduling | Cron/event-driven scheduling; priority queues | Nov | 2 |  | Not Started | 0
2.2.10 | Finding Dedup & Correlation | Cross-scanner deduplication; correlate SAST+SCA+secrets | Nov | 2 |  | Not Started | 0
2.2.11 | Testing & QA | OWASP Benchmark; FP rate < 15% target | Nov | 1 |  | Not Started | 0
TOTAL |  |  |  | 27 |  |  | Weighted Avg

## F10
F10: Pipeline Policy-as-Code Enforcement (Advanced)
Org-wide CI/CD validation, auto-correction of pipelines, SBOM/provenance/signature enforcement.
Value: Supply chain security at scale. Automated enforcement replaces manual audit checklist reviews.
Phase | Phase 2 | Timeline | Aug - Nov | Tasks | 10 | Total Weight | 22 | Owner | ___________
Task ID | Task Name | Description | Month | Weight | Owner | Status | Completion %
2.3.1 | Org-Wide Policy Management | Hierarchical policies: org -> team -> repo with override/merge | Aug | 3 |  | Not Started | 0
2.3.2 | Pipeline Auto-Correction Engine | AI-generated pipeline patches; PR-based workflow | Aug-Sep | 3 |  | Not Started | 0
2.3.3 | SBOM Generation Enforcement | Require CycloneDX/SPDX SBOM; validate completeness | Sep | 2 |  | Not Started | 0
2.3.4 | Provenance Verification Engine | SLSA provenance verification; build attestation | Sep-Oct | 3 |  | Not Started | 0
2.3.5 | Artifact Signature Enforcement | Require Sigstore/Cosign signatures | Oct | 2 |  | Not Started | 0
2.3.6 | Policy Violation Alerting | Real-time alerts; escalation chains; SLA tracking | Oct | 2 |  | Not Started | 0
2.3.7 | Compliance Reporting Dashboard | SOC 2 / ISO / NIST evidence generation | Oct-Nov | 2 |  | Not Started | 0
2.3.8 | Policy Versioning & Rollback | Git-backed versioning; rollback; audit log | Nov | 2 |  | Not Started | 0
2.3.9 | Exception Management Workflow | Request/approve/expire exception workflow | Nov | 2 |  | Not Started | 0
2.3.10 | Testing & QA | Test across 100+ pipeline configurations | Nov | 1 |  | Not Started | 0
TOTAL |  |  |  | 22 |  |  | Weighted Avg

## F11
F11: AI-Driven Inventory & SBOM Platform
Agent-based application discovery, dependency health scoring, vulnerability correlation, license tracking.
Value: Know what you have before you can secure it. Automated inventory eliminates shadow IT blind spots.
Phase | Phase 2 | Timeline | Sep - Dec | Tasks | 10 | Total Weight | 23 | Owner | ___________
Task ID | Task Name | Description | Month | Weight | Owner | Status | Completion %
2.4.1 | Agent-Based Application Discovery | Scan org repos for tech stacks / frameworks / services | Sep | 3 |  | Not Started | 0
2.4.2 | Automated SBOM Generation | CycloneDX + SPDX from source / manifests / containers | Sep-Oct | 3 |  | Not Started | 0
2.4.3 | Dependency Health Scoring | Score: maintenance / vulns / license risk / age / popularity | Oct | 3 |  | Not Started | 0
2.4.4 | Vulnerability Correlation Engine | Cross-reference NVD / OSV / GitHub Advisory / vendor feeds | Oct-Nov | 3 |  | Not Started | 0
2.4.5 | License Tracking & Compliance | Detect license types; flag copyleft; compliance reports | Nov | 2 |  | Not Started | 0
2.4.6 | Dependency Graph Visualization | Interactive tree with vuln/license overlays | Nov | 2 |  | Not Started | 0
2.4.7 | Risk-Based Vuln Prioritization | EPSS + reachability + exploit maturity scoring | Nov-Dec | 2 |  | Not Started | 0
2.4.8 | Inventory Management Dashboard | Unified catalog: stack / owner / risk / SBOM freshness | Dec | 2 |  | Not Started | 0
2.4.9 | Automated Update Recommendations | AI-suggested updates with breaking change assessment | Dec | 2 |  | Not Started | 0
2.4.10 | Testing & QA | Validate against known vulnerable dependency sets | Dec | 1 |  | Not Started | 0
TOTAL |  |  |  | 23 |  |  | Weighted Avg

## F12
F12: Advanced VS Code IDE Plugin (V2)
Broader language support, real-time AI remediation, intelligent code analysis, risk profile integration.
Value: Security intelligence directly in the developer's flow. One-click auto-fix turns security findings into immediate actions.
Phase | Phase 2 | Timeline | Sep - Dec | Tasks | 10 | Total Weight | 21 | Owner | ___________
Task ID | Task Name | Description | Month | Weight | Owner | Status | Completion %
2.5.1 | Extended Language Support | Java / Go / C# / Ruby / PHP / Kotlin analysis | Sep-Oct | 3 |  | Not Started | 0
2.5.2 | Real-Time AI Remediation Engine | Context-aware fix generation with codebase understanding | Oct | 3 |  | Not Started | 0
2.5.3 | Intelligent Code Analysis | Semantic taint tracking / data flow in IDE | Oct-Nov | 3 |  | Not Started | 0
2.5.4 | Risk Profile Integration | Project risk score / findings in sidebar | Nov | 2 |  | Not Started | 0
2.5.5 | Inline Threat Context Overlay | Threat model -> code mapping in editor | Nov | 2 |  | Not Started | 0
2.5.6 | AI Code Review Assistant | Pre-commit security review; risk summary | Nov-Dec | 3 |  | Not Started | 0
2.5.7 | Team Security Metrics Widget | Team fix rate / open vulns / score panel | Dec | 1 |  | Not Started | 0
2.5.8 | One-Click Auto-Fix | Apply AI fixes with diff preview | Dec | 2 |  | Not Started | 0
2.5.9 | Marketplace V2 Publishing | Listing update; V1 migration guide | Dec | 1 |  | Not Started | 0
2.5.10 | Testing & QA | Cross-language; <500ms target | Dec | 1 |  | Not Started | 0
TOTAL |  |  |  | 21 |  |  | Weighted Avg

## Timeline
Feature ID | Feature Name | Phase | Tasks | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
F1 | Security Requirements Generation | Phase: Phase 1; Tasks: 13
F2 | Misuse / Abuse Case Generation | Phase: Phase 1; Tasks: 9
F3 | Security Acceptance Criteria | Phase: Phase 1; Tasks: 8
F4 | AI-Assisted Threat Modeling (L0 & L1) | Phase: Phase 1; Tasks: 11
F5 | Commit Scanner | Phase: Phase 1; Tasks: 10
F6 | Pipeline Policy-as-Code Validator | Phase: Phase 1; Tasks: 11
F7 | VS Code Plugin (Initial Version) | Phase: Phase 1; Tasks: 10
F8 | Full AI Threat Modeling | Phase: Phase 2; Tasks: 12
F9 | Secure Development Intelligence | Phase: Phase 2; Tasks: 11
F10 | Pipeline Policy-as-Code Enforcement (Advanced) | Phase: Phase 2; Tasks: 10
F11 | AI-Driven Inventory & SBOM Platform | Phase: Phase 2; Tasks: 10
F12 | Advanced VS Code IDE Plugin (V2) | Phase: Phase 2; Tasks: 10

## Monthly Tracking
Monthly Completion Tracking (Fill in % per feature each month)
Formula: Feature % = SUM(task_weight x task_%) / SUM(task_weights) ¦ Phase % = AVG(feature %s)
Feature ID | Feature Name | Phase | Tasks | Weight | Feb % | Mar % | Apr % | May % | Jun % | Jul % | Aug % | Sep % | Oct % | Nov % | Dec %
F1 | Security Requirements Generation | Phase 1 | 13 | 32
F2 | Misuse / Abuse Case Generation | Phase 1 | 9 | 20
F3 | Security Acceptance Criteria | Phase 1 | 8 | 17
F4 | AI-Assisted Threat Modeling (L0 & L1) | Phase 1 | 11 | 26
F5 | Commit Scanner | Phase 1 | 10 | 22
F6 | Pipeline Policy-as-Code Validator | Phase 1 | 11 | 24
F7 | VS Code Plugin (Initial Version) | Phase 1 | 10 | 20
F8 | Full AI Threat Modeling | Phase 2 | 12 | 30
F9 | Secure Development Intelligence | Phase 2 | 11 | 27
F10 | Pipeline Policy-as-Code Enforcement (Advanced) | Phase 2 | 10 | 22
F11 | AI-Driven Inventory & SBOM Platform | Phase 2 | 10 | 23
F12 | Advanced VS Code IDE Plugin (V2) | Phase 2 | 10 | 21
OVERALL |  |  | 127 | 284

## Monthly Workload
Month | Phase | Active Tasks | Features Active | Cumulative Milestone
Feb | Phase 1 | 9 | F1, F2, F4 | Research complete; architecture parser; ASVS mapping engine prototype
Mar | Phase 1 | 16 | F1, F2, F3, F4, F5 | Core AI engines working end-to-end
Apr | Phase 1 | 20 | F1-F7 | Integrations live; commit scanner real-time; pipeline parser working
May | Phase 1 | 22 | F1-F7 | All Phase 1 features functional; testing underway
Jun | Phase 1 | 11 | F4, F6, F7 | Phase 1 GA release
Jul | Phase 2 | 5 | F8, F9 | Deep analysis engines; SAST engine prototype
Aug | Phase 2 | 10 | F8, F9, F10 | DFD generation; SCA; org policies
Sep | Phase 2 | 14 | F8-F12 | L2 threats; SBOM; language expansion
Oct | Phase 2 | 15 | F8-F12 | Attack paths; auto-fix PRs; AI code analysis
Nov | Phase 2 | 17 | F8-F12 | Dashboards; compliance; code review assistant
Dec | Phase 2 | 8 | F11, F12 | Phase 2 GA release